## Matrix
RACI Matrix JCC HANA Migration Project |  | JCC | Vendor
Deliverable or Task
1 | Provide requisite connectivity and network infrastructure | R | C
2 | Submit all Templates and Report Formats to JCC for preapproval prior to first submission. | C | A
3 | Evaluation of the existing test cases & update test cases | R | C
4 | HANA migration of SAP ECC, Solution Manager, SAP BW and Portal | C | A
5 | Execute Prechecks | C | R
6 | Review Prechecks | C | R
7 | Preconversion Configuration | C | R
8 | Code Remediation | C | R
9 | Upgrade & DB Conversion | C | R
10 | Database installation/patches, SAP software installation, Client/System Refresh | C | R
11 | Post Conversion Configuration | C | R |  |  | Should we add:
12 | Testing (Regression/Integration/UAT) of remediated code | C | R |  |  | Other test phases - regression/ integration/ UAT?
13 | Testing (Regression/Integration/UAT) of Interfaces | C | R |  |  | Knowledge Transfer Plan/execution
14 | Simplification Workshops | C | R |  |  | Post go-live functional configuration/support
15 | Security Enablement Workshop | C | R
16 | Security Execution | C | R
17 | Analytics Enablement Workshop | C | R
18 | Fiori Enablement Workshop | C | R
19 | Organizational Change Management | R | C
20 | End User Training | R | C
21 | Disaster Recovery Setup and Configuration | C | R
22 | Issue Tracking and resolution | C | R | JCC s/b C?
23 | Project Plan | C | R
24 | Project Governance | C | R
25 | Identify the key stakeholders and decision makers and provide reasonable access to all stakeholders and other relevant personnel as required during the engagement for clarification of questions, issue resolution, and reviews | R | I |  | Legend
26 | Project Management | C | R |  | R | Responsible
27 | Project Metrics and Status Reporting | I | R |  | A | Accountable
28 | Ownership of deliverables committed in the project scope | I | A |  | C | Consulted
29 | Knowledge Transfer Planning and Execution | C | A
30 | Post-Go-Live Functional Configuration and Support | C | A
31 | Review and sign-off on deliverables | R | I |  | I | Informed
Insert new rows above this one
R | Responsible
A | Accountable
C | Consulted
I | Informed