## Deliverable Costs
Exhibit 3
Cost Worksheet
Judicial Branch Data Warehouse and Data Integration Services
The Contractor shall furnish all labor, materials, and equipment necessary to perform the Project in accordance with the specifications described in Exhibit 1, Statement of Work, at the all-inclusive rates. The hourly rates shall be fully burdened and inclusive of all costs including, but not limited to personnel, materials, computer support, commissions, travel, lodging, per diem, and overhead rates payable to the Contractor for services rendered. The Contractor shall not charge, nor shall the Judicial Council pay any overtime rate.
Submission of this information is mandatory.
RQM-ID | Services | Hours | Hourly Rate | Cost Not to Exceed
Not to Exceed
Design and Development
RQ-001 | Design, develop, and test a new data set for the CARE Act data from existing mental health case type schema with possible new data elements added to existing data dictionary, JCC standardized values, and/or reference table mapping
Design, develop and deployment of data marts and data warehouse schemas
Design, development and deployment of the data sharing and data integration between participating parties
Design, development and deployment of data collection and transformation (ELT/ETL process)
Design, development and deployment of data dashboards and reports
Create new PowerBI dashboards and/or reports for CARE Act reporting
RQ-002 | Design, develop, and test a new data set CMHS from existing mental health case type schema with possible new data elements added to existing data dictionary, JCC standardized values, and/or reference table mapping
Design, development and deployment of the data sharing and data integration between participating parties
Design, development and deployment of data collection and transformation (ELT/ETL process)
Design, development and deployment of data dashboards and reports
Create new PowerBI dashboards and/or reports for Community Mental Health Act reporting
RQ-003 | Update configuration to allow four new appellate courts to leverage existing dashboards and reports
RQ-004 | Incorporate database/data structure design based on the fields identified by the project stakeholders and team members.
RQ-005 | Design and develop reports and dashboards with appropriate row and field level security built in to ensure restricted access based on roles
RQ-006 | Provide knowledge transfer, training, documentation and turnover to parties identified by Agency/Courts
RQ-007 | Perform thorough testing and quality assurance of the end-to-end solution
RQ-008 | Support user acceptance testing
RQ-009 | Perform/support transition to production (Go-Live)
RQ-010 | Design and develop fact and dimensions tables into the branch wide cloud data warehouse, e.g., Snowflake
RQ-011 | Integrate with branch-wide identity management platform.
RQ-012 | Create initial dashboards and reports with appropriate NIST RBAC model of RBAC (Role-Based Access Control) and demonstrate the security aspects.
RQ-013 | Define and develop strategy plan document
RQ-014 | Configure and secure automated batch data exports
Total
RQM-ID | Services | Hours | Hourly Rate | Cost Not to Exceed
Not to Exceed
Onboarding new courts
RQ-015 | Onboard 6 additional courts to the Platform complying with the following protocol:
RQ-016 | Setup technology & data integration framework for each of the participating courts
RQ-017 | Initial Set up of Snowflake tenant
RQ-018 | Talend installation
RQ-019 | Power BI Dashboard set up
RQ-020 | Data dictionary/query review
RQ-021 | Work with Subject Matter Experts (SMEs) to collect, develop, refine and document the requirements and help negotiate the implementation scope, timeline pertaining to:
RQ-022 | 1. Business processes
RQ-023 | 2. Data sources and their transformation/enrichment rules/expectations
RQ-024 | Testing for each case type - including quality assurance and User Accceptance testing
RQ-025 | Perform/support transition to production (Go-Live)
RQ-026 | Onboard four (4) Appellate Courts to Platform with the following components included in the scope/deliverables:
RQ-027 | Architecture Support – Talend/Metadata Updates
RQ-028 | DW Code Updates for each district
RQ-029 | Load case-level and SRL data for the onboarding courts and the new datasets into a centralized data warehouse for analytics and business intelligence dashboards
RQ-030 | Incorporate the new court participants into existing dashboards (set up and access for 8 existing dashboards).
RQ-031 | Setup and create separate data warehouse tenants for the participating courts.
RQ-032 | Setup the administration and management of each tenant by each participating court.
RQ-033 | Securely configure environments
RQ-034 | Utilize established interface(s) for the real-time consumption of data from participating courts.
RQ-035 | Integrate participating court with the branch-wide identity management platform (Azure AD).
Total
RQM-ID | Services | Hours | Hourly Rate | Cost Not to Exceed
Not to Exceed
Project Management
RQ-036 | Manage development, daily stand ups, sprint planning, story assignment and related processes; release management.
RQ-037 | Provide Project management artifacts and deliverables, including:
RQ-038 | Project Charter
RQ-039 | Project Plan
RQ-040 | Project Quality Assurance (QA) Plan
RQ-041 | Project Schedule
RQ-042 | Communication Plan
RQ-043 | Key Milestones
RQ-044 | Project budget
RQ-045 | Initial RAID (Risks, Actions, Issues, and Dependencies) Log
RQ-046 | Weekly, monthly and quarterly Status Reports as needed
RQ-047 | Requirements Traceability Document (RTM)
RQ-048 | Interface Master List
RQ-049 | CARE ACT High-Level Design Document
RQ-050 | Community Mental Health High-Level Design Document
RQ-051 | Appellate Court High Level Code Update Requirements
RQ-052 | Manage Contractor Staffing Plan.
RQ-053 | Manage Change Management Plan
RQ-054 | Provide Impact Analysis Document
Total
RQM-ID | Services | Hours | Hourly Rate | Cost Not to Exceed
Not to Exceed
Support and Maintenance
RQ-055 | Integrate courts runtime environments into the JCC's central, cloud based data integration environment utilizing Talend, Snowflake and related interfacing mechanisms
RQ-056 | Utilize established ETL/ELT designs and pipelines for loading historical data from multiple source systems into Snowflake environments.
RQ-057 | Utilize established, Power BI based data visualization and reporting to support court onboarding.
RQ-058 | Maintain and support the setup and configuration of Snowflake instances at individual courts and at JCC, build data warehouse/Share-house and establish appropriate DB link, Shared DataMart for collaboration between JCC and courts. Perform regular maintenance, upkeep, performance tuning and provide DBA support for Snowflake instances and tenants used by the JCC and courts. Monitor the utilization of the compute nodes and recommend optimizations based on the current and projected workloads.
RQ-059 | Maintain, setup of Talend/ETL infrastructure for JCC and individual courts including on premise components, cloud components, while implementing security mechanisms viz. VPN, VPC etc., RBAC mechanisms using SSO, Azure AD following the established JCC security guidelines
RQ-060 | Maintain and support the implemented data integration/ETL pipelines to bring data from court system into JCC data warehouse.
RQ-061 | Maintain and support the reporting infrastructure, create/load/import users and user profiles, their access levels. Implement security mechanism for collaboration with Azure AD and SSO (Single Sign On).
RQ-062 | Maintain, update, develop reports and dashboards using the established reporting framework and infrastructure. Publish them to the authorized personnel/group of receivers with appropriate access levels. Ensure the dashboards and reports meet or exceed the SLAs by conducting ongoing query performance tuning.
RQ-063 | Maintain and create task scheduling, job dependency management and task automation such that the ongoing operational tasks are automated, and the end-to-end system can function with least manual intervention and supervision. Operationalize periodic data loads and remove manual intervention and implement alerting mechanism in case of system failure.
RQ-064 | Maintain and support DevOps and CI/CD pipelines for build, release and operational. management, with built in automated log capture, log monitoring and alerting mechanisms.
RQ-065 | Utilize the established end-to-end Data Analytics and Data Integration platform and processes to support the branch (JCC) and the participating CA courts, while recommending improvements and enhancements and implementing the approved changes.
RQ-066 | Utilize standard supported integration interfaces to support automated data collections, e.g., cloud-based data storage exchange, support via secure file transfer, support for web services (REST API and SOAP) integration, and through via messaging-based services.
RQ-067 | Follow established continuous integration/continuous deployment (CI/CD), DevOps/DataOps, automated environment best practices utilizing modern SDLC techniques for all new development efforts including enhancements and defect fixes.
RQ-068 | Develop and maintain solution to measure data load metrics over time along with a dashboarding and alerting mechanism to report variances
RQ-069 | Periodically report platform's performance/reliability metrics and improvement plans in case of performance degradation
RQ-070 | Incorporate feedback resulting from any digital security activities such as audits, threat modeling, Penetration testing etc. of the platform and perform in any relavant remediation and testing activities
RQ-071 | Maintain the appropriate and current levels of security patches on all the platform components and ensure the critical digital security vulnerabilities are prevented
Total
RQM-ID | Services | Hours | Hourly Rate | Cost Not to Exceed
Not to Exceed
Termination Assistance
RQ-072 | Provide a Termination Assistance plan.
RQ-073 | Provide all information, documentation, tools, and other materials created or updated regarding or relating to this contract
Total
Training
RQ-074 | Train JBE personnel in the support of the Platform integration with Judicial Branch IDMS/AD Services.
RQ-075 | Provide UAT training.
RQ-076 | Populate training environment with Council-specific data and initial transaction data to support training delivery and user scenarios, if needed based on training strategy.
RQ-077 | Store all training material and recorded media in a knowledge central repository accessible by Council support Personnel.
RQ-078 | Deliver Transition & Training to M&O Support & Council support staff.
Total
Contract Total