## Table 1
| Judicial Council of California | [7 empty] | Author: Paul Menard
| Capital Program Summary | [7 empty] | 2015-12-28
| County | Capital Project Name | Capital Project Status | Courtroom Count | Building Area SF | Total Project Cost | Construction Start | Construction Finish | Construction Duration Days
1 | Butte | New Chico Courthouse | Construction completed in first quarter of 2015 | 5 | 65096 | 65064000 | 2013-05-02 | 2015-03-31 | 698
2 | Riverside | New Banning Justice Center | Construction completed in second quarter of 2015. | 6 | 68584 | 63261000 | 2012-03-20 | 2015-04-30 | 1136
3 | San Joaquin | Renovate and Addition to Juvenile Justice Center | Construction completed in second quarter of 2015. One courtroom was added to two existing courtrooms for a total of three. | 1 | 3495 | 3774000 | 2014-04-01 | 2015-05-31 | 425
|  |  | Completed in FY 2014-2015 – Totals | 12 | 137175 | 132099000
4 | Yolo | New Woodland Courthouse | Construction completed in third quarter of 2015 | 14 | 163066 | 161452000 | 2013-04-15 | 2015-07-31 | 837
5 | Madera | New Madera County Courthouse | Construction completed in third quarter of 2015 | 10 | 115804 | 100208000 | 2012-08-06 | 2015-09-30 | 1150
6 | Kings | New Hanford Courthouse | Construction began in August 2013 and is scheduled to complete in fourth quarter of 2015 | 12 | 144460 | 124329000 | 2013-07-01 | 2015-12-24 | 906
7 | Sutter | New Yuba City Courthouse | Construction began in August 2013 and is scheduled to complete in fourth quarter of 2015 | 7 | 73853 | 65834000 | 2013-07-01 | 2015-12-31 | 913
8 | Santa Clara | New Santa Clara Family Justice Center | Construction began in August 2013 and is scheduled to end in first quarter of 2016 | 20 | 233906 | 233267000 | 2013-09-01 | 2016-04-30 | 972
|  |  | Completed in FY 2015-2016 – Totals | 63 | 731089 | 685090000
9 | Tehama | New Red Bluff Courthouse | Construction began in December 2014 and is scheduled to complete in third quarter of 2016 | 5 | 62033 | 57822000 | 2014-12-01 | 2016-09-30 | 669
10 | Merced | New Los Banos Courthouse | Construction began in May 2015 and is scheduled to complete in third quarter of 2016 | 2 | 29511 | 26680000 | 2015-06-01 | 2016-10-31 | 518
11 | San Joaquin | New Stockton Courthouse | Construction began in June 2014 and is scheduled to end in fourth quarter of 2016 | 30 | 310443 | 272939000 | 2014-04-01 | 2016-12-31 | 1005
12 | San Diego | New Central San Diego Courthouse | Construction began in December 2013 and is scheduled to end in fourth quarter of 2016 | 71 | 704000 | 555499000 | 2014-01-03 | 2017-05-30 | 1243
13 | Alameda | New East County Courthouse | Construction began in August 2014 and is scheduled to end in first quarter of 2017 | 13 | 146435 | 147683625 | 2015-02-01 | 2017-06-30 | 880
|  |  | To Be Completed in FY 2016-2017 – Totals | 121 | 1252422 | 1060623625
14 | Glenn | Renovate and Addition to Willows Courthouse | In working drawings; construction to start in FY 2015–2016 and is scheduled to end in fourth quarter of 2017 | 3 | 41867 | 42932000 | 2016-04-01 | 2018-03-31 | 729
|  |  | To Be Completed in FY 2017-2018 – Totals | 3 | 41867 | 42932000
15 | Siskiyou | New Yreka Courthouse | In working drawings; start construction in FY 2015–2016 | 5 | 67459 | 69653000 | 2016-07-01 | 2018-09-30 | 821
16 | Los Angeles | Hollywood Courthouse | Design/Build project to be submitted for FY 2016–2017 funding | 4 | 45000 | 47273000 | 2017-04-01 | 2019-03-31 | 729
17 | Imperial | New El Centro Courthouse | In working drawings; construction requested in FY 2016–2017 | 4 | 47512 | 46465000 | 2017-04-01 | 2019-06-30 | 820
18 | Riverside | New Indio Juvenile and Family Courthouse | In working drawings; construction requested in FY 2016–2017 | 5 | 54967 | 52634000 | 2016-12-01 | 2019-06-30 | 941
|  |  | To Be Completed in FY 2018-2019 – Totals | 18 | 214938 | 216025000
19 | Lake | New Lakeport Courthouse | In working drawings; start construction in FY 2016–2017 | 4 | 45300 | 49688000 | 2017-07-01 | 2019-12-31 | 913
20 | Tuolumne | New Sonora Courthouse | In design; proceed with working drawings in FY 2015–2016; construction requested in FY 2017–2018 | 5 | 61537 | 69236000 | 2017-07-01 | 2020-01-31 | 944
21 | Shasta | New Redding Courthouse | In preliminary design; proceed with working drawings and demolition of existing structures on new courthouse site (using construction phase funding of $0.174 million) in FY 2015–2016; construction requested in FY 2017–2018 | 14 | 166296 | 155759000 | 2017-07-01 | 2020-05-31 | 1065
|  |  | To Be Completed in FY 2019-2020 – Totals | 23 | 273133 | 274683000
22 | Sonoma | New Santa Rosa Criminal Courthouse | In design; proceed with working drawings in FY 2017–2018 | 15 | 169342 | 178689000 | 2018-02-01 | 2020-12-31 | 1064
23 | Stanislaus | New Modesto Courthouse | Design to begin FY 2015–2016; working drawings requested in FY 2016–2017 | 26 | 301464 | 277164000 | 2018-05-01 | 2021-03-31 | 1065
24 | Riverside | New Mid-County Civil Courthouse | In design; site acquisition and preliminary plans reappropriated in FY 2015–2016; working drawings requested in FY 2016–2017 | 9 | 89690 | 92515000 | 2018-12-01 | 2021-05-31 | 912
25 | Sacramento | New Sacramento Criminal Courthouse | In preliminary design; proceed with preliminary plans and working drawings using one-time funds authorized by AB 1476. The construction phase has not yet been funded. | 44 | 405500 | 451959000 | 2018-07-01 | 2021-06-30 | 1095
|  |  | To Be Completed in FY 2020-2021 – Totals | 94 | 965996 | 1000327000
26 | El Dorado | New Placerville Courthouse | In site acquisition; site acquisition and preliminary plans reappropriated in FY 2015–2016; working drawings requested in FY 2016–2017 | 6 | 77559 | 91073000 | 2019-07-01 | 2021-09-30 | 822
27 | Mendocino | New Ukiah Courthouse | In site acquisition; design to start in FY 2015–2016 and working drawings requested in FY 2016–2017 | 8 | 90206 | 94451000 | 2018-07-01 | 2021-09-30 | 1187
28 | Santa Barbara | New Santa Barbara Criminal Courthouse | In design; proceed with working drawings and demolition of existing structures on new courthouse site (using construction phase funding of $0.400 million) in FY 2015–2016 | 8 | 92331 | 99507000 | 2018-12-01 | 2022-01-19 | 1145
29 | Inyo | New Inyo County Courthouse | In site acquisition; site acquisition and preliminary plans reappropriated in FY 2015–2016 | 2 | 21015 | 33704000 | 2020-02-01 | 2022-03-31 | 789
|  |  | To Be Completed in FY 2021-2022 – Totals | 24 | 281111 | 318735000
30 | Los Angeles | New Eastlake Juvenile Courthouse | In site acquisition; site acquisition reappropriated in FY 2015–2016 | 5 | 57799 | 90312000 | 2020-10-01 | 2022-12-31 | 821
|  |  | To Be Completed in FY 2022-2023 – Totals | 5 | 57799 | 90312000
|  |  | JCC Capital Program Totals FY 2014-2015 through FY 2022-2023 | 363 | 3955530 | 3820826625
Indefinitely Delayed
| County | Capital Project Name | Indefinitely-Delayed Capital Project Status
31 | Fresno | Renovate Fresno County Courthouse | Indefinitely delayed as of Judicial Council Meetings on October 26, 2012, and January 17, 2013.
32 | Kern | New Delano Courthouse
33 | Kern | New Mojave Courthouse
34 | Los Angeles | New Glendale Courthouse
35 | Los Angeles | New Santa Clarita Courthouse
36 | Los Angeles | New Southeast Los Angeles Courthouse
37 | Monterey | New South Monterey County Courthouse
38 | Nevada | New Nevada City Courthouse
39 | Placer | New Tahoe Area Courthouse
40 | Plumas | New Quincy Courthouse