## Summary
1.0 Implementation and Deployment Services Overview
Exhibit 2 Implementation and Deployment Services Requirements sets forth the roles and responsibilities of the parties for the Application Implementation and Deployment Services to be provided. These are the services required to devise a well thought out and thorough approach, a standards and best practices based methodology and deployment plan, and a successful deployment of the application. The Implementation and Deployment Services shall include, but are not limited to the following: • Preliminary Business Analysis Services • Implementation Strategy and Approach Services • Deployment Planning Services • Deployment including: o Implementation Project Management Services o Infrastructure Assessment Services o Operational Processes & Procedures Services o Application Configuration Services o Data Conversion Services o Data Integration Services o Document Management System Configuration Services o Testing Services o Cutover and Stabilization Services o Training Services • Implementation Project Management Services o Demonstrated ability in large deployment projects using Project Management best practices o Proven methodologies for application project strategy development
Instructions: Tab 2 Implementation & Deployment Services - Please provide response to the questions. The Proposer may attach any additional pages required to fully address any of the requirements, provided each addition page is clearly labeled with the requirement number and category name/description to which it applies.
Instructions: Tab 3 Requirements, Tab 4 Service Levels, Tab 5 Definitions - JCC considers Proposer to agree to Exhibit 2, unless identified herein. Absence of issues will constitute agreement for those terms not herein addressed, and will be off the table for further negotiation.

## Implem. & Deploy Srvs
2.0 Implementation and Deployment Services
All Implementation and Deployment Services are mandatory. Response: In-Progress requires a comment and estimated delivery date. Please note: inability to deliver requirements may be considered a non-responsive bid.
Item # | Implementation and Deployment Services | Response Yes/No/ In-Progress | Comments
2.1 | Describe your implementation planning process (including project management, best practices, Organizational Change Management, Communications, and Personnel management). Provide a sample plan with timelines.
2.2 | Describe your recommendation for roles your company personnel will assume and the roles that JBEs and third party business partners should assume in the implementation process, as well as, the process for replacing implementation personnel.
2.3 | Describe how your proposed management practices, procedures and tools conform to industry best practices and describe the benefits of your approach. Include coordination and control of deployment activities in order to identify and mitigate issues; overall approach to communication at all levels for the life of the project; organizational change management process; staffing level management process and personnel management process.
2.4 | Describe how you would manage the use of any required interfaces or electronic tools that have been purchased and/or installed.
2.5 | Describe the process involved in implementing any required specific configurations, e.g., California/County retirement files, deferred compensation reports, and child support payments sent to California State Disbursement Unit. Identify any local personnel required to accomplish the task.
2.6 | Describe the process, resources, File Transfer Protocol (FTP), and expertise necessary in converting data from existing system into the new application. Include any limitations.
2.7 | Describe your process for coordinating user acceptance. Identify how issues with validation of historical data conversion is handled.
2.8 | Describe your process for communicating and implementing change management.
2.9 | Describe how out-of-scope items are communicated and remediated.
2.1 | Describe your process for managing critical defect scenarios.
2.11 | Describe your process for coordinating software upgrades and version management.
2.12 | Describe the process employed to track and report progress, including the plan to keep the project on-time.
2.13 | Describe the process and standards employed in determining when phases of deployment are satisfactorily completed.
2.14 | Describe the implementation training approach, include formats (instructor lead, on-site, in-person, online, etc.), resources (templates, reference manuals, etc.), and customer expectations.
2.15 | Describe the post implementation support and issue resolution provided to achieve a smooth transition from the legacy system to the new, with error free payroll cycles (e.g., 90-day post implementation support).
2.16 | Describe the process involved in implementing any required federal, state and local configurations, e.g., implementation of federal/state statutes and rules, etc. Include any local personnel required to accomplish the task.
2.17 | Describe the process involved in assessing and recommending how the required hardware and software will ensure improved performance for the end-users is achieved, and how it is scalable to meet future human capital management needs.

## Requirements
3.0 Implementation and Deployment Services
The following sections set forth the Vendor’s tasks, roles and responsibilities and the services for which the Vendor shall be responsible. The JBE's roles and responsibilities may include or be assigned to a third party business partners as part of a seperate agreement, MOU or other mutually agreed upon instrument.
3.1 | Preliminary Business Analysis Services tasks, roles and responsibilities. Preliminary Business Analysis Services include the tasks, activities and deliverables required by the Vendor to gain sufficient knowledge about the JBE and overall requirements to enable creation of an implementation strategy and approach, a deployment plan, and to successfully deploy the Application. The following table identifies the Vendor’s and JBE's Preliminary Business Analysis Services tasks, roles and responsibilities. | Vendor | JBE | Issue | Proposed Solution/Rationale & Benefit to the JBE
| 1. Participate in meetings with the JBE, third party business partners to understand high-level requirements, priorities, and existing team and reporting structure within the organization. | X
| 2. Deliverable: Develop and present to a Preliminary Business Analysis Plan that clearly highlights the Vendor recommended steps to obtain the required knowledge to start the deployment process. This plan should clearly articulate the key steps that will be performed by the Vendor for obtaining requisite knowledge as well as lay out the time and effort requirements from the JBE. | X
| 3. Review, approve, and accept the Preliminary Business Analysis Plan. |  | X
| 4. Execute the Preliminary Business Analysis Plan and obtain the required knowledge to start the deployment process. | X
| 5. Deliverable: Document the results of Preliminary Business Analysis and present to JBE. | X
| 6. Review, approve, and accept the results of the Preliminary Business Analysis. |  | X
3.2 | Implementation Strategy and Approach Services Tasks, Roles and Responsibilities. Implementation Strategy and Approach Services are the activities and Deliverables associated with developing, refining the deployment, and training strategy approach and methodology that will be used for deployment of the proposed solution. The following table identifies the Vendor’s and JBE’s Implementation Strategy and Approach Services tasks, roles, and responsibilities | Vendor | JBE | Issue | Proposed Solution/Rationale & Benefit to the JBE
| 1. Deliverable: Document and present to JBE the recommended Implementation Strategy and Approach, including a communication plan that accounts for all constituents (e.g., JBEs, and third party business partners, etc.) and a technical environment plan that includes the scope and objectives of non-production and production environments. | X
| 2. Review, approve and accept the recommended implementation strategy and approach, communication plan, and technical environment plan. |  | X
| 3. Deliverable: Develop a Vendor Staffing Plan that identifies vendor staff levels required at various points in the project and supports the implementation strategy and approach. | X
| 4. Review, approve and accept the Vendor Staffing Plan. |  | X
| 5. Deliverable: Recommend a JBE and/or third party business partner Vendor Staffing Plan that identifies staff levels required at various points in the project and that will support the implementation strategy and approach. | X
| 6. Deliverable: Develop and present a detailed, standards-based methodology with proposed toolsets to complete this deployment initiative within time and budget. | X
| 7. Review, approve and accept the methodology and toolsets for deploying the application. |  | X
| 8. Deliverable: Provide recommendations on appropriate deployment of logical environments to support vendor’s recommended deployment strategy (e.g., testing, data conversion, etc.) | X
| 9. Review, approve and accept recommendations on appropriate deployment environments. |  | X
3.3 | Implementation Services
The Deployment Services are those services, as described in the following subsections that must be performed to successfully deploy the Application.
3.3.1 | Implementation Requirement: Implementation/Deployment Project Management Services
Deployment Project Management Services are the activities and Deliverables associated with developing and maintaining an Implementation/Deployment project Plan and schedule for deployment of the application. The following table identifies the Vendor’s and JBE’s Deployment Planning Services tasks, roles and responsibilities.
| Implementation/Deployment Project Management Services Tasks, Roles and Responsibilities | Vendor | JBE | Issue | Proposed Solution/Rationale & Benefit to the JBE
| 1. Deliverable: Develop, document and maintain the Implementation/Deployment Project Plan throughout the course of the engagement. This plan is based on the approved overall approach, methodology and use of proposed toolsets and processes. Vendor shall update this plan on a periodic basis as defined by JBE (e.g., monthly, bi-monthly). This plan shall be developed and maintained in Microsoft Project software or an alternative project management tool approved by JBE. This plan shall include all required details such as staffing, timelines, key activities, milestones, deliverables, actual progress against plan, variances, etc. Implementation/Deployment Project Plan will take into consideration JBE holidays. Provide timelines for off-the-shelf product implementation, as well as, California specific enhancement release timeline. | X
| 2. Review, approve and accept Implementation/Deployment Project Plan |  | X
| 3. Establish, maintain and update a Deployment Knowledge Base with all deliverables and documents within the scope of the Deployment Services. In addition to full and accurate documentation of the Vendor's own activities, Vendor will include in the Deployment Knowledge Base all documents, information and data on which they rely to perform Deployment Services, including but not limited to the following: configuration guides, training manuals, assessment reports, user manuals, system level setup and procedures, all queries, form templates, reports and tuning parameters around the database or servers. The Deployment Knowledge Base must be fully indexed and key word searchable. | X
3.3.2 | Deployment Requirements: Infrastructure Assessment and Implementation Services
Infrastructure Assessment and Implementation Services are the activities and Deliverables required to assess and to validate that all components of the HRIS technical infrastructure, which must be able to support the Application, and the traffic generated through their use. These components include, but are not limited to, desktops, laptops, network elements, scanners, printers, etc. Infrastructure Assessment and Implementation Services also include coordinating and managing the implementation of other needed components. The following table identifies the Vendor’s and JBE's Infrastructure Assessment and Implementation Services tasks, roles and responsibilities.
Vendor’s Infrastructure Assessments and Deployment Services will focus on evaluating JBE'S infrastructure in four main areas:
1. Desktop Environment – Evaluation of desktop machines and devices, Operating System (OS), and required software components and printers.
2. Network Environment – Evaluation of bandwidth and capacity planning capabilities against anticipated traffic volumes due to implementation of the Application, Interfaces, and projected growth.
3. Data Center Environment – Vendor will evaluate JBE connectivity and environment readiness (e.g., Application, Interfaces, Data Exchange Infrastructure, etc.) based on the infrastructure recommendations from the Deployment Strategy and Approach and Planning phases.
In addition, during the Infrastructure Assessment, Vendor will identify gaps, formulate recommendations, and communicate an action plan for JBE to address the findings in the Infrastructure Assessment. Information will be shared with the JBE at regular and pre-defined stages of the Assessment. Vendor will deliver the final Infrastructure Assessment Findings report to the JBE for review and approval.
| Infrastructure Assessment and Implementation Services Tasks, Roles and Responsibilities | Vendor | JBE | Issue | Proposed Solution/Rationale & Benefit to the JBE
| 1. Deliverable: Develop and document an Infrastructure Assessment Plan and template for assessing all components of HCM technical infrastructure. | X
| 2. Review, approve and accept the Infrastructure Assessment Plan and template. |  | X
| 3. Perform the infrastructure assessment for all technical components for HCM Services. | X
| 4. Deliverable: Document and present the findings of the infrastructure assessment, including recommendations on specific areas that need to be upgraded, standardized or secured. | X
| 5. Review, approve and accept the findings of the infrastructure assessment. |  | X
| 6. Perform hardware and connectivity capacity planning for HCM Services. | X
| 7. Review, approve and accept hardware and connectivity capacity planning. |  | X
| 8. Deliverable: Document and present an assessment of required hardware as well as the network infrastructure required at a minimum to support the rollout. | X
| 9. Review, approve and accept the hardware and network infrastructure assessment. |  | X
| 10. Manage the installation of any additional hardware or network infrastructure and coordinate with third parties as required. |  | X
| 11. Review, approve and accept the installed hardware or network infrastructure. | X
| 12. Measure bandwidth utilization and minimum hardware required to support rollout. | X
| 13. Deliverable: Provide documented findings of the minimum requirements for desktop hardware along with bandwidth utilization numbers to support sizing of the network to the hosting data center. | X
| 14. Review, approve and accept documented findings. |  | X
3.3.3 | Deployment Requirement: Operational Process and Procedures Services
Operational Process and Procedures Services are the activities and Deliverables required to assess the existing processes and procedures, perform a gap analysis with the process options compatible with the Application and develop and document recommended case management operational processes and procedures that will be utilized with the Application. Identify out of scope items.
| Operational Processes and Procedures Services Tasks, Roles and Responsibilities | Vendor | JBE | Issue | Proposed Solution/Rationale & Benefit to the JBE
| 1. Identify current operational processes and procedures used for HCM by working in conjunction with the JBE and third party business partners. | X
| 2. Deliverable: Assess the existing (“as is”) operational processes and procedures against the end state (“to be”) Application configurations, processes and procedures, develop recommendations on processes that will meet requirements, and include out of scope items. | X
| 3. Review, approve and accept the “as is” versus “to be” assessment and the process recommendations. |  | X
| 4. Deliverable: Document approved procedures in an approved format. | X
| 5. Review, approve and accept approved procedures. |  | X
| 6. Deliverable: Develop and provide a business impact analysis based on the “as is” versus “to be” assessment. | X
| 7. Review, approve and accept the business impact analysis. |  | X
3.3.4 | Deployment Requirement: Application Configuration Services
Application Configuration Services are the activities and deliverables required to configure the Application to support business processes. The following table identifies the Vendor’s and JBE's Application Configuration Services tasks, roles and responsibilities.
| Application Configuration Services Tasks, Roles and Responsibilities | Vendor | JBE | Issue | Proposed Solution/Rationale & Benefit to the JBE
| 1. Conduct training sessions/system walkthroughs for JBE staff to provide an understanding of the application and business context for configurations. | X
| 2. Conduct SME Education Sessions about system and configuration impacts. | X
| 3. Identify end state (“to be”) configurations by working in conjunction with the JBE and third party business partners. | X
| 4. Deliverable: Develop a detailed application configuration strategy that will meet requirements. | X
| 5. Review, approve and accept the “as is” versus “to be” assessment and the configuration strategy. |  | X
| 6. Deliverable: Develop and document a detailed application configuration plan that links to data exchange configuration. | X
| 7. Review, approve and accept the detailed application configuration plan. |  | X
| 8. Deliverable: Create and maintain a detailed application configuration workbook incorporating all recommended Configuration Items (CIs). | X
| 9. Review, approve and accept the detailed application configuration workbook. |  | X
| 10. Configure approved CIs as documented in the detailed application configuration workbook into the Application. | X
| 11. Deliverable: Create and submit a detailed configuration workbook listing the final Application configuration, including any out of scope items. | X
| 12. Review, approve and accept the configuration workbook. |  | X
| 13. Perform Application Configuration Services activities in synchronization with the Data Integration Services | X
| 14. Identify Forms, Notices, and Reports requirements and design by working in conjunction with the JBE and third party business partners. | X
| 15. Deliverable: Forms, Notices, and Reports Design Documents |  | X
| 16. Review, approve and accept Forms, Notices, and Reports Design Documents. | X
| 17. Test approved configurations based on the Detailed Application Configuration Workbook. Unit test the configuration. | X
| 18. Identify defects and changes. |  | X
| 19. Remediate identified defects and changes. | X
3.3.5 | Deployment Requirement: Data Conversion Services
Data Conversion Services are the activities and Deliverables associated with the assessment, planning, mapping, scripting, conversion and testing required for the conversion of data from the current systems to the Application. The following table identifies the Vendor’s and JBE's Data Conversion tasks, roles and responsibilities.
| Data Conversion Services Tasks, Roles and Responsibilities | Vendor | JBE | Issue | Proposed Solution/Rationale & Benefit to the JBE
| 1. Identify sources of data from the current systems by working in conjunction with the JBE and/or third party business partners. | X
| 2. Deliverable: Assess the existing (“as is”) sources of data (including software, code, functionality, and data) against the end state (“to be”) Application, and develop a detailed Data Conversion Strategy and Data Conversion Plan for each source of data based on the assessment | X
| 3. Review, approve and accept the detailed Data Conversion Strategy and Data Conversion Plan. |  | X
| 4. Deliverable: For each source of data, develop and document the detailed data schema/maps from current systems to the Application. | X
| 5. Deliverable: For each source of data, identify and document data elements which cannot be converted through the automated tools and/or other exceptions and develop a plan to achieve data conversion through alternative means (e.g., manual conversion, manual entry). | X
| 6. Review, approve and accept mapping and plan for converting data elements which cannot be converted through automated tools and/or other exceptions. |  | X
| 7. Configure data conversion tools, as required to perform data conversion. | X
| 8. Provide all relevant technical documentation (development/configuration manuals etc.) on such data conversion scripts and tools. | X
| 9. Perform data conversion through automated or manual processes as approved by JBE. | X
| 10. Deliverable: Create a comprehensive Data Conversion Test Plan for each source of data. | x
| 11. Review, approve and accept all Data Conversion Test Plans. |  | X
| 12. Deliverable: Conduct data conversion testing using Vendor’s validation process, identify errors and exceptions and document and provide a report on the testing results to JBE. | X
| 13. Conduct data conversion re-testing until requirements are met. | X
| 14. Review, approve and accept conversion testing and retesting results. |  | X
3.3.6 | Deployment Requirement: Data Integration Services
Data Integration Services are the activities and Deliverables associated with the assessment, planning, design, development, modification, and testing of the data exchanges between the JBE and third party business partners, and the Application. This includes third party business partner exchanges and electronic services, as well as the Application portal. The following table identifies the Vendor’s and JBE’s Data Integration Services tasks, roles and responsibilities.
| Data Integration Services Tasks, Roles and Responsibilities | Vendor | JBE | Issue | Proposed Solution/Rationale & Benefit to the JBE
| 1. Create an inventory of data exchanges (local and outside exchanges) including internal, third party business partners, vendor exchanges and portal access, and create a Gap Analysis that assesses the existing (“as is”) state and scope of exchanges against the end state (“to be”) and scope of exchanges. | X
| 2. Identify data exchange requirements between the current JBE and partner systems and the Application, and analyze them against proposed data exchange standards, access requirements, etc. and present recommended exchanges to the JBE. | X
| 3. Ensure that such data exchange requirements between the JBE and partner systems and the Application are identified by working in conjunction with the JBE and thid party business partners (e.g., county, benefit administrators, retirement agencies). Additionally, ensure that any gaps or exceptions identified in configuration or data conversion affecting data exchanges as well as deficiencies in the data exchange standards are also assessed. | X
| 4. Deliverable: Develop and provide to JBE, a Gap Analysis that includes recommendations on the new exchanges that need to be configured and developed. | X
| 5. Review, approve and accept the Gap Analysis. |  | X
| 6. Discuss Gap Analysis results with third party business partners. | X
| 7. Deliverable: Develop and maintain a detailed Data Exchange Deployment Plan consisting of the end-to-end process for exchange deployment (from the “as is” to the “to be” states) including organization of local data exchange deployment team, including JBE, Vendor and third party business partner resources, as needed. | X
| 8. Review, approve and accept the detailed Data Exchange Deployment Plan |  | X
| 9. Deliverable: Develop and maintain a data integration pre-testing activities workbook including connectivity of vendors/partners, development of JBE policy file, and configuration of exchanges. | X
| 10. Review, approve, and accept the pre-testing activities workbook. |  | X
| 11. Perform the necessary activities to configure and deploy exchanges as required and approved by the JBE. | X
| 12. Deliverable: Conduct data exchange deployment (for both local and third party exchanges) and integration testing using Vendor’s validation process, identify errors and exceptions and document and provide testing and traceability matrix results to JBE. | X
| 13. Conduct data exchange deployment and integration re-testing until requirements are met. | X
| 14. Review, approve and accept data exchange deployment and integration testing and retesting results. |  | X
| 15. Provide JBE with one data integration technical subject matter expert, as requested by the JBE. | X
| 16. Perform Data Integration Services activities in synchronization with the Application Configuration Services. | X
3.3.8 | Implementation Requirement: Testing Services
Testing Services are the activities and Deliverables associated with planning and executing testing for Acceptance by the JBE of the entire set of contracted Deployment requirements (e.g., configuration, exchanges). The following table identifies the Vendor’s and JBE’s Testing Services tasks, roles and responsibilities.
| Testing Services Tasks, Roles and Responsibilities | Vendor | JBE | Issue | Proposed Solution/Rationale & Benefit to the JBE
| 1. Deliverable: Develop, document and maintain a Test Plan for all Deployment Services, including the plan for end-to-end testing, network performance testing, data integration testing, application configuration testing, roles-based access testing, and Acceptance testing. The Test Plan will define criteria for entering and exiting the various test phases. | X
| 2. Review, approve and accept the Test Plan. |  | X
| 3. Prepare and document test cases, test scripts and test data as required by the Test Plan. | X
| 4. Review, approve and accept test cases, test scripts, and test data. |  | X
| 5. Deliverable: Perform end-to-end testing, network performance testing, data integration testing, application configuration testing, mock cutover testing, and roles-based access testing, using industry standard methodologies and best practices. Such testing shall include testing for any and all Application release versions issued prior to Final Acceptance of the Services. | X
| 6. Support Acceptance testing processes. | X
| 7. Conduct Acceptance testing. |  | X
| 8. Deliverable: Manage, identify, classify, and document any Deployment Services-related deficiencies or errors found as a result of testing, using prescribed tools. | X
| 9. Resolve Deployment requirements-related deficiencies and errors found as a result of testing. Such Resolution shall include retesting. | X
| 10. Deliverable: Document and provide the testing and retesting and traceability matrix results for approval. | X
| 11. Develop any additionally needed test scripts for any subsequent Application releases prior to a Final Acceptance of the Services. | X
| 12. Review, approve and accept testing, retesting and traceability matrix results. |  | X
3.3.9 | Implementation Requirement: Cutover and Stabilization Services
Cutover and Stabilization Services are the activities and Deliverables required to successfully manage the Cutover from existing systems to the Application (“go live” support) without affecting the day-to-day functioning and ensuring that the transition process to the Application is completed quickly and in the most efficient manner possible. The following table identifies the Vendor’s and JBE’s Cutover and Stabilization Services tasks, roles and responsibilities.
| Cutover and Stabilization Services Tasks, Roles and Responsibilities | Vendor | JBE | Issue | Proposed Solution/Rationale & Benefit to the JBE
| 1. Deliverable: Define and document the Cutover and Stabilization Services Plan to be performed by Vendor. | X
| 2. Review, approve, and accept the Operational Cutover and Stabilization Services Plan. |  | X
| 3. Perform and coordinate cutover activities in accordance with the Cutover and Stabilization Services Plan. | X
| 4. Provide expert on-site support to JBE personnel during the Cutover, to ensure that the Cutover and transition are performed smoothly. | X
| 5. Provide expert on-site resolution of any issues or problems that may arise in the post-Cutover transition stabilization period and/or manage resolution through approved processes and procedures. | X
| 6. Perform all activities as provided, at minimum, in the defined exit criteria. | X
| 7. Coordinate with JBE help desk as required, including problem management and Incident management processes. | X
| 8. Train help desk and provide requisite help desk scripts and tools for Deployment Services and daily support and maintenance. | X
| 9. Review, approve, and accept scripts. |  | X
3.3.10 | Implementation Requirement: Training Services
Training Services are the activities and Deliverables associated with training the Application configuration administrators and End-Users for the purpose of supporting the Application and fully utilizing the functions and features of the applications through formal training (which may include classroom training, computer or web based training) and informal methods during the Deployment. The following table identifies the Vendor’s and JBE’s Training Services tasks, roles and responsibilities.
| Training Services Roles and Responsibilities | Vendor | JBE | Issue | Proposed Solution/Rationale & Benefit to the JBE
| 1. Deliverable: Develop, document and maintain a Training Plan, including training schedule, instructor requirements, facilitator requirements, module/class structure, facilities requirements, alternative facility options, specific training data issues, and identify if using training partners. | X
| 2. Review, approve and accept the Training Plan. |  | X
| 3. Deliverable: Provide Application configuration and administration training to administrators. | X
| 4. Deliverable: Provide Application End-User training and help desk training. | X
| 5. Deliverable: Provide ongoing, pre-scheduled Application End-User training and help desk training for any subsequent Application releases prior to Final Acceptance of the Services. | X
| 6. Create and maintain the training configurations on the Application training instances as requested. | X
| 7. Deliverable: Provide specified End-Users with ongoing, pre-scheduled operational training for any subsequent Application releases prior to Final Acceptance of the Services. | X
| 8. Review, approve, and accept training. |  | X
3.4 | Implementation Requirement: Project Management Services
Implementation Project Management Services are the activities and Deliverables associated with providing project management throughout the term of the engagement. The following table identifies the Vendor’s and Court’s Implementation Project Management Services tasks, roles and responsibilities.
| Implementation Project Management Services Tasks, Roles and Responsibilities | Vendor | Court | Issue | Proposed Solution/Rationale and Benefit to the Court
| 1. Provide project strategy and direction including overall scope and timelines. |  | X
| 2. Provide, and review with JBE, Vendor project metrics reporting on Vendor’s accomplishment of milestones, SLRs and associated Deliverables. | X
| 3. Review, approve and accept project metrics, SLRs, milestones and Deliverables. |  | X
| 4. Develop and present remediation plans to resolve Deployment Services related issues. | X
| 5. Review, approve and accept remediation plans to resolve Deployment Services related issues. |  | X
| 7. Coordinate the Application releases between the pre-production environments to the production environment. | X
| 8. Participate as requested in technical and business planning/governance meetings to establish and communicate decisions. | X
| 9. Adhere to Incident and problem management processes and tools. | X
| 10. Vendor Project Manager shall schedule and conduct weekly project status meetings with appropriate Vendor resources in accordance with the Project Communications Plan with Court Project Manager and other key participants as the Project Manager may require. | X
| 11. Participate in weekly project status report meetings. |  | X
| 12. Deliverable: Provide written weekly project status reports to the JBE Project Manager including status updates of applicable items in the Project Plan (e.g. the project schedule) in a format agreed to by JBE, including escalation of any issues and risks that may impact Critical Milestones, as well as issue and risk mitigation actions. | X
| 13. Execute projects using PMI best practices including standard project life cycle activities, project initiation, planning, execution, control and closure, and Acceptance. | X
| 14. Coordinate all Services, activities and dependencies and serve as the single point of contact/interface to JBE including coordinating Vendor, Third Party and Court resources to ensure the on-time delivery of tested/quality checked Deliverables as defined in the Project Plan. | X
| 15. Prepare and present a quarterly Executive Management Report in a mutually agreed upon format. | X
| 16. Deliverable: Provide a Change Management Plan outlining the review process for documenting and approving changes in project scope. | X
| 17. Provide single portal access for all documents and reports | X
| 18. Provide a regular Implementation Summary Report that includes current status of milestones and all SLRs. | X
| 19. Review, approve and accept Implementation Summary Report. |  | X
| 20. Deliverable: Develop overall approach and strategy to manage and maintain a Deployment Knowledge Base that will contain deployment documents and Deliverables from deployment, including recommendations on content, structure and tools. | X
| 21. Review, approve and accept overall approach and strategy to manage and maintain a Deployment Knowledge Base. |  | X
| 22. Deliverable: Manage and maintain the specified Deployment Knowledge Base throughout the Application deployment process, incorporating Application documents and Deliverables. | X
| 23. Deliverable: Update the Deployment Knowledge Base with all deliverables and documents as a part of Cutover and Stabilization Services. | X
| 24. Review, approve and accept the updated Deployment Knowledge Base after all deliverables and documents. |  | X

## Service Levels
4.0 Service Level Requirements
A key objective of this outsourcing agreement is to attain Service Level Requirements (SLRs). SLRs associated with Deployment Services are detailed in the following section.
Vendor shall provide electronic reports to the JBE regarding Vendor’s compliance with the SLRs specified in the Master Services Agreement.
Table 1. Variance to Deployment Plan SLRs
Definition | Measurement of the variance between the Vendor and JBE agreed completion dates of key project activities, milestones and Deliverables identified in the Deployment Plan and actual completion dates.
Type | Service Measure | Performance Target | SLR Performance
Adherence to Deployment Plan Key Activities and Milestones | Variance from Deployment Plan | Variance of key activities and milestones dates < 10% | 100%
| Formula | (Number of milestone dates missed)/Total number of milestone dates
| Measurement Interval | Measure Bi-weekly
| Reporting Period | Report Bi-weekly
| Measurement Tool | TBD
Table 2. Post Deployment Incident Resolution SLRs
Definition | Time to Resolve Incidents and Problems to different Priority Level classifications following Incident classification as a configuration/implementation Incident. This pertains to Incidents and problems occurring between the “Go-Live” date and the end of the Cutover period for the JBE.
Incident Resolution SLRs
Incident Resolution | Service Measure | Performance | SLR Performance %
Target
Severity 1 or 2 Incident Notification | Time to respond | < 15 minutes | All 100% ONLY
Severity Level 1 | Time to Resolve | < 4 hours | 100%
Severity Level 2 | Time to Resolve | < 8 hours | 100%
Severity Level 3 | Time to Resolve | < 40 hours | 100%
Severity Level 4 | Time to Resolve | 15 days | 90%
Root Cause Analysis | Time to report | Within 24 hours of Incident Resolution for Priority Level 1 or 2 | 100%
| Formula | Number of requests completed within performance target/total of all requests occurring during Measurement Interval
| Measurement Interval | Measure Weekly
| Reporting Period | Report Monthly
| Measurement Tool | TBD
Table 3. Priority Levels
Priority Level | Description
1 - Emergency/Urgent | A Priority Level 1 Incident is generated if it is an incident based on configuration, data conversion, data exchange or FNR (Forms, Notices and Reports) activities and has severely impacted the application or component such that the application or component cannot reasonably continue to operate and there is no Workaround available.
2 - High | A Priority Level 2 Incident is generated if it is an incident based on configuration, data conversion, data exchange or FNR (Forms, Notices and Reports) activities and has severely impacted the application or component such that the application or component cannot reasonably continue to operate, but a Workaround is available.
3 - Medium | A Priority Level 3 Incident is generated if it is an incident based on configuration, data conversion, data exchange or FNR (Forms, Notices and Reports) activities and has impacted the application or component such that the non-critical component of the application is unavailable, will not work or is not operating as expected and there is a Workaround available.
4 - Low | A Priority Level 4 Incident is generated if there is a Problem other than Priority Level 1, Priority Level 2, and Priority Level 3 Incidents.

## Definitions
5 | Requirements Definitions
5.1 | Application - the complete Human Capital Management (HCM) application, including all associated software, data exchanges, and external systems to be implemented by vendor.
5.2 | Training Plan - the plan the vendor shall develop for conducting end-user and configuration administrator Application training.
5.3 | Critical Milestones - those milestones, activities, actions and projects identified as such in this Agreement, but are not limited to this Agreement. Additional milestones may be negotiated by individual JBE.
5.4 | Customer Satisfaction - a subjective rating obtained through customer satisfaction surveys conducted from time to time in accordance with terms defined herein.
5.5 | Cutover - going-live on the Application, at one or more locations, and where all personnel who are provided access to the HCM system(s) are able to access the Application and perform their normal daily operations using the production environment of the Application.
5.6 | Final Acceptance - written Acceptance of all Services and Deliverables including signoff on all exit criteria as defined in the Cutover and Stabilizations Services.
5.7 | Incident - either a (i) single event or (ii) abnormal activity for a function monitored by vendor, each requiring a vendor response typically denoted by a request for service or identification of a problem. JBE or designee will determine the Incident Priority Level of each reported incident. Vendor will provide an escalation procedure (to be approved by JBE) for resolution of reported and non-reported incidents.
5.8 | Incident Resolution - the point at which the vendor has responded to an Incident and has either: (a) conducted and successfully completed a Root Cause Analysis on a problem and appropriately corrected both the results and the cause of the problem; or (b) has provided an appropriate answer to an inquiry or an informational question that is understood by and acceptable to JBE or designee. In both cases, the Incident is not resolved until JBE or designee is convinced and satisfied that it has been resolved.
5.9 | Implementation and Deployment Project Plan - plan the vendor shall develop with respect to the Implementation and Deployment Services, as defined in Exhibit 2.
5.1 | Knowledge Transfer Plan - plan the vendor shall develop and execute transferring the knowledge required for vendor to start the implementation process, as defined in Exhibit 2.
5.11 | Measurement Interval - the period in which a given SLR is measured (e.g., one (1) month, one (1) year, etc.).
5.12 | Measurement Tool - a tool used to measure processes, equipment, and network systems.
5.13 | Performance Target - is defined as the desired level of service JBE or designee is seeking for that particular Service Level Requirement.
5.14 | Priority Level - a defined category that identifies the degree of business criticality and importance of specific Incidents and the associated vendor response requirements attributed to any such Incident. The Priority Level table categories and descriptions set forth in Exhibit 2 apply to all Services.
5.15 | Reporting Period - the interval of time between providing reports. Unless otherwise specified, all reports are provided on a bi-weekly basis within three (3) Business Days of the close of the reporting period.
5.16 | Resolve or Resolution - to repair, replace, reconfigure, reinstall, re-route, or otherwise provide a complete solution to an Incident that returns the system and/or end-user(s) to non-degraded full functionality. Implementing a workaround is a partial or temporary resolution.
5.17 | Root Cause Analysis - a problem analysis process undertaken to identify and quantify the underlying cause(s) of an Incident and document the necessary corrective actions to be taken to prevent recurring problems and/or trends which could result in problems.
5.18 | Implementation Plan - the plan for deployment of the Application that the vendor shall develop and maintain throughout the course of the Implementation/Deployment Services in accordance with Exhibit 2.
5.19 | Workaround - a temporary solution that vendor, JBE, or third party business partner can implement in the event of an Incident as an alternate method of providing full Service or process functionality that allows the affected system(s) and/or process(es) to deliver to JBE an acceptable level of business operations functionality until a permanent Incident Resolution can be implemented. Any such Workaround must be acceptable to and approved by JBE.